The Climate Investment Funds — Investment Plans, Delivery and Disbursement

How the pipeline works, where it sticks, and the reforms underway to fix it.

KEY ABBREVIATIONS

ACT: Accelerating Coal Transition Program MDB: Multilateral Development Bank, AMPLIFi: New CIF modality to mobilize private capital at scale, NPC: Nature, People and Climate Program, ARISE: Next-generation resilience investment program (2025), PPCR: Pilot Program for Climate Resilience, CCMM: CIF Capital Markets Mechanism, REI: Renewable Energy Integration program, CIF: Climate Investment Funds, SCF: Strategic Climate Fund, CTF: Clean Technology Fund, SREP: Scaling Up Renewable Energy Program (low-income countries), DESNZ: UK Dept. for Energy Security and Net Zero, TFC: Trust Fund Committee, FCDO: UK Foreign, Commonwealth & Development Office, TIP: Transitional Investment Plan (proposed), FIP: Forest Investment Program

INTRODUCTION

The Climate Investment Funds (CIF) are the largest multilateral climate fund by contributions on record, with $13.2 billion pledged since 2008 and a portfolio now reaching over 80 countries. CIF has no agency-accreditation gate of the kind that shapes the GEF or GCF — six AAA-rated multilateral development banks (MDBs) are its permanent delivery partners. The comparable bottleneck instead sits in the Investment Plan pipeline: the sequence a country must clear from expression of interest to first disbursement. CIF's headline efficiency — a 1:10 co-financing ratio and a disbursement ratio around 61–66% — compares favourably with the GCF and GEF, but a post-endorsement bottleneck rooted in MDB loan mechanics, and a rising share of delayed projects, mean money still reaches the ground more slowly than the top-line numbers suggest.

KEY STATISTICS AT A GLANCE

| $13.2B Total contributions Plus $0.5B in CCMM bond proceeds, Dec 2025 | 1:10 Co-financing ratio $9.4B approved → $98.6B expected co-financing | 61% Disbursement ratio $5.7B disbursed of $9.4B approved, AR2025 | 82% CTF projects on track Down from 91% in 2023 — rising delivery risk | 6 MDB delivery partners World Bank, IFC, ADB, AfDB, EBRD, IDB Group | $500M CCMM inaugural bond 6x oversubscribed, $3B orderbook, Jan 2025 |
| --- | --- | --- | --- | --- | --- |

THE FUND: STRUCTURE AND RECENT PERFORMANCE

CIF operates through two sub-funds: the Clean Technology Fund (CTF), which supports middle-income countries to deploy low-carbon technology at scale, and the Strategic Climate Fund (SCF), an umbrella for programmes serving mainly lower-income countries — forestry (FIP), renewable energy access (SREP), adaptation (PPCR, now succeeded by ARISE), industrial decarbonisation, and nature (NPC). Of $9.4 billion CIF-approved funding, $6.9 billion sits in CTF and $2.5 billion in SCF. Renewable energy dominates the sector split at $3.9 billion, and Asia and Sub-Saharan Africa together account for roughly half of regional allocation. Administratively, CIF is lean: admin costs run at 2.6% of cumulative funding decisions against 3.4% for the GCF and 3.7% for the GEF, and MDB implementation fees of 0.7–3.9% undercut the GCF (7.95%) and GEF (9.5%) by a wide margin. In January 2025, CIF became the first multilateral climate fund to raise capital directly from bond markets through the CIF Capital Markets Mechanism (CCMM), unlocking reflows from the CTF loan book rather than relying solely on donor replenishment.

THE INVESTMENT PLAN PIPELINE: FOUR STAGES

| Stage 1 — Call & Expression of Interest - CIF issues a call (e.g. Industry Decarbonization Program, Oct 2024); countries submit EOIs, often jointly with private-sector partners and an MDB. - Secretariat and Trust Fund Committee screen for relevance, readiness and geographic balance. 24 countries submitted EOIs for Industry Decarbonization by Jan 2025; 7 selected by June 2025. | Stage 2 — Co-development - CIF, the government and partner MDB run scoping missions, technical workshops and public consultation to draft the Investment Plan. - Cross-cutting themes (just transition, gender, Indigenous engagement) are built in at this stage, not bolted on later. Rwanda's plan involved a two-day field mission plus Kigali workshops before June 2024 endorsement. | Stage 3 — Endorsement - The relevant Trust Fund Committee (CTF or SCF) formally endorses the Investment Plan and its funding envelope. - This is the closest CIF equivalent to an accreditation gate — it is programme-level, not institution-level. $860M endorsed for 8 countries in 2024; $321M endorsed in 2025. | Stage 4 — MDB Approval & Disbursement - Individual projects go through the delivery MDB's own appraisal, procurement and board-approval process. - Funds disburse against milestones once the MDB's own financing (often a sovereign loan) is signed. CTF disbursement ratio: 55% (2021) → 66% (2024) — improving, but from a low base. |
| --- | --- | --- | --- |

CHALLENGES: APPROVAL MOMENTUM VS. DELIVERY REALITY

Pre-endorsement performance has genuinely improved — post-endorsement is where delivery now strains:

- MDB loan-linkage bottleneck. CIF grants for MDB-delivered projects are tied to that bank's own sovereign loan and internal board approval. Until the loan is signed, the grant cannot disburse — even if the project is otherwise ready.

- Co-financing lock-in. Commitment letters are required at endorsement, fixing resources 2–3 years before implementation starts; any change triggers resubmission, adding delay just as a plan nears disbursement.

- Infrastructure-scale lag. Large projects typically take five-plus years to fully disburse. Over 20% of CTF projects approved 2009–2019 needed extensions, mostly for procurement or restructuring.

- Rising implementation risk. Projects rated “on track” fell from 91% (2023) to 82% (2024) — 29 flagged delayed — even as the disbursement ratio kept climbing. The two metrics diverge, and on-track share is the leading indicator.

- Long-tail results reporting. Emissions reductions accrue over an asset's lifetime, not the investment period: CTF had reduced only ~11% of its lifetime GHG target cumulatively even where installed capacity tracked much closer to plan.

- Reallocation friction. When a country steps back — India declined to develop an ACT Investment Plan in late 2024 — the earmarked funds ($500M) need a formal reallocation process that can itself take a year or more.

CTF disbursement ratio, by year (portfolio-wide)

| 2020 | 2021 | 2022 | 2023 | 2024 | Target trend |
| --- | --- | --- | --- | --- | --- |
| 46% | 55% | 55% | 61% | 66% | Improving, ~5pp/yr |

Source: UK DESNZ/FCDO CIF Annual Review 2024/25. Disbursement ratio has improved steadily but remains well below full portfolio maturity; 53 of the roughly 154 tracked CTF projects (about $1.76bn in commitments) were fully disbursed as of mid-2024.

WHAT REVIEWS HAVE ALREADY IMPROVED

- Investment Plan Close-Outs (2024, new practice). Six close-out workshops — PPCR in Zambia and the Caribbean, FIP in Indonesia, Brazil and the DRC, SREP in the Maldives — converted implementation experience into documented lessons rather than letting it disappear at project end. Zambia reached 234% of its resilience target; the Maldives lifted renewable share from 11% to 24%.

- Independent evaluations. A midterm evaluation of the Forest Investment Program and a 2025 evaluation of the Pilot Program for Climate Resilience (PPCR) directly shaped the design of CIF's successor programmes — the Nature, People and Climate (NPC) programme and ARISE respectively.

- Governance streamlining (2024). CIF collapsed its sub-committee structure into three Trust Fund Committees (Joint, CTF, SCF), reducing duplicated sign-off and speeding decision cycles.

- Capital-market diversification. The CCMM bond (Jan 2025) reduces CIF's dependence on donor replenishment cycles by recycling CTF loan reflows into fresh finance — a genuinely new lever, not a tweak to the existing one.

REFORMS AND PROPOSED REFORMS

| Underway - ARISE — next-generation resilience programme building directly on PPCR's evaluated lessons; $100M in early German and Spanish contributions. - Industry Decarbonization Program — up to $250M per country with a mandatory private-sector carve-out, designed to pull in co-investors from the outset rather than after endorsement. - AMPLIFi — a new modality announced in 2025 to mobilise private capital at higher leverage ratios than CIF's current 1:10 average. | Proposed / recommended by donors - Transitional Investment Plans (TIPs) — the next evolution of the country-plan model, designed for multi-government, regional-scale planning. - Formal fast-track policy for reprogramming cancelled or unallocated funds, rather than case-by-case negotiation. - A refreshed results framework (logframe) to replace outdated indicators and close the one-year data lag in donor reporting. |
| --- | --- |

RECOMMENDATIONS

- De-link, where feasible, CIF grant effectiveness from the delivery MDB's sovereign loan signature, so grant components can proceed in parallel rather than waiting on bank-internal timelines.

- Replace single up-front co-financing lock-in with phased commitment letters tied to implementation milestones, reducing the resubmission risk that currently follows any change in a co-financier's position.

- Make the Investment Plan Close-Out model standard practice across all programmes, not a rolling pilot, so lessons are captured before institutional memory is lost.

- Track the on-track/at-risk share — not only the disbursement ratio — as the headline delivery indicator, given the two measures diverged sharply between 2023 and 2024.

- Adopt a standing fast-track policy for reallocating cancelled or unallocated country envelopes, cutting the multi-year gap currently seen between a country stepping back and funds being redeployed.

- Scale CCMM- and AMPLIFi-style capital-market mechanisms deliberately, using them to smooth the funding cycle rather than treating them as one-off innovations.

SOURCES

1.  CIF Annual Report 2024, “Shifting Gears” (cif.org).

2.  CIF Annual Report 2025, “Roots for Resilience and Ambition” (cif.org).

3.  UK Department for Energy Security and Net Zero / FCDO, Climate Investment Funds (CIF) Annual Review 2024/25, Programme ID GB-GOV-13-ICF0004-CIF.