Research Report.

GCF Accreditation to Disbursement: Barriers, Reforms, and the Next Steps.

List of Abbreviations

Abbreviations: AADFI: Assoc. of African Development Finance Institutions, AEs: Accredited Entities, AF: Adaptation Fund, AP: Accreditation Panel, COP: Conference of the Parties, DAEs: Direct Access Entities, DFIs: Development Finance Institutions, EDA: Enhanced Direct Access, ESS: Environmental & Social Safeguards, FAA: Funded Activity Agreement, GCF: Green Climate Fund, GEF: Global Environment Facility, IAEs: International Access Entities, IEU: Independent Evaluation Unit, IFRS: International Financial Reporting Standards, IPSAS: International Public Sector Accounting Standards, LDCs: Least Developed Countries, MAF: Monitoring & Accountability Framework, NDAs: National Designated Authorities, NDCs: Nationally Determined Contributions, NCQG: New Collective Quantified Goal on Climate Finance, PPF: Project Preparation Facility, PSAA: Project-Specific Assessment Approach, RAF: Revised Accreditation Framework, SAP: Simplified Approval Process, SIDS: Small Island Developing States, UNFCCC: UN Framework Conv. on Climate Change, VCEF: Vertical Climate and Environmental Funds

| USD 20.10bn 350 projects & programmes approved, 134 countries (GCF, 2026) | USD 6.7bn Disbursed, ~32% of approvals. | 80% of approved funding via 55 IAEs; 113 DAEs share just 20% - despite being 67% of AEs | 876 grants USD 740.71m readiness approved across 142 countries; USD 537m disbursed (GCF, 2026) |
| --- | --- | --- | --- |

1.  Introduction: The GCF and the Accreditation Requirement

The Green Climate Fund (GCF) is the world's largest dedicated multilateral climate fund, established under the UNFCCC to channel resources from developed to developing countries for climate mitigation and adaptation. All organisations wishing to receive GCF funds must first be accredited; a formal institutional due diligence process assessing whether an entity can manage GCF resources in line with the Fund's fiduciary standards, Environmental and Social Safeguards (ESS), and gender policy. This requirement applies to governments, national Development Finance Institutions (DFIs), civil society organisations, and private sector entities alike. Accreditation is therefore the gateway through which all climate finance flows, and it has become one of the most contested features of the climate finance architecture. The five-step pathway under the Revised Accreditation Framework (RAF), effective October 2025, is illustrated below:

| GCF Accreditation Process — Five-Step Pathway ¦ Revised Accreditation Framework (RAF), Decision B.42/13, Effective October 2025 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| STEP 1 Government Nomination or Self-Nomination NDA endorsement required for DAEs. IAEs and private sector may self-nominate. | ▶ | STEP 2 Pre-Screening Open year-round. Checks eligibility, legal personality, and capacity before formal application. | ▶ | STEP 3 Application & Fees 2 annual two-month windows. Full documentation submitted. Fees payable on completion. | ▶ | STEP 4 Screening & Review 9-month target. Fiduciary, ESS, and gender policy review by Secretariat and AP. | ▶ | STEP 5 Board Decision & Certificate AP recommends; Board approves. Certificate issued. No re-accreditation required under RAF. |
| Three mandatory assessment pillars applied across all stages: Fiduciary Standards (B.07/02) · Environmental & Social Safeguards (ESS) · Gender Policy |  |  |  |  |  |  |  |  |

| 2. Accreditation: Nature, Challenges and Barriers The GCF fiduciary standards require applicants to demonstrate IFRS or IPSAS-compliant financial management, independent internal and external audit, procurement frameworks, anti-money laundering and whistleblower policies, ESS frameworks, and gender action plans. For most national DFIs in Sub-Saharan Africa and SIDS, these represent institutional gaps that take years to address. Capacity gap (AADFI Mapping, 2024): While 87.5% of African DFIs incorporate climate finance in their annual planning and 72.5% engage in climate change projects, only 7.5% have achieved GCF accreditation, 2.5% GEF accreditation, and 2.5% Adaptation Fund (AF) accreditation. Only 60% have a dedicated monitoring desk, and only 40% have staff with climate finance expertise yet 87.5% want capacity-building. This gap between aspiration and institutional readiness is the central barrier. Scalar barriers: Treichel et al. (2024) show that accreditation standards are predicated on largeness and do not reflect SIDS realities. The IEU reported an average 506-day processing time. Only 7 of 63 national-level accredited entities were based in SIDS across only 6 of 40 SIDS countries, despite SIDS representing 25% of eligible nations. Transaction cost trap: The AADFI survey identifies the accreditation process as "long, complicated, complex, and human-capital intensive." DFIs must hire external consultants to rewrite policies, draft compliance manuals, and audit trails costs that frequently outweigh certainty of capital access. Language barriers further disadvantage Francophone and Lusophone institutions. Country ownership deficit: 57.5% of DFIs engaged in climate projects work closely with their NDA, while 42.5% do not. CSOs in Cameroon and Malawi (Germanwatch, 2022) confirmed that NDAs signed no-objection letters without understanding project implementation arrangements, leaving countries listed in the GCF portfolio but receiving no finance. The "Catch-22": the GCF requires track records in climate instruments that most national DFIs have never managed. | 3. The Revised Accreditation Framework (RAF): What Changed At Board Meeting 42 in July 2025, the GCF adopted the RAF (decision B.42/13); the most substantial overhaul since the Fund's establishment, effective 31 October 2025. It is a six-component, interdependent reform covering the accreditation framework, screening requirements, fees policy, updated MAF, flexible legal arrangements, and a policy coherence analysis. Key improvements: Two structured two-month application windows per year replace the unpredictable rolling queue. A nine-month review target compresses a process that previously lasted 2-3 years. Re-accreditation is abolished - accreditation is now indefinite subject to the updated MAF. Specialised fiduciary standards for on-lending and blending are deferred to the project proposal stage. Legal arrangements are simplified: accreditation takes effect via certificate on Board approval, replacing the Accreditation Master Agreement. Expanded access provisions: Pre-screening is now year-round, allowing entities to identify gaps before the formal timed cycle begins. Fast-track accreditation for entities already vetted by the GEF or AF is expanded. Fee discounts are introduced for national and regional applicants from LDCs and SIDS. The PSAA pilot allows one project submission without full institutional accreditation. Remaining concerns: GCFWatch (2026) warns the two-month screening response window may be insufficient for capacity-constrained DFIs. The structural imbalance persists: 80% of approved GCF funding still flows through international AEs. The revised MAF removes the re-accreditation requirement for AEs to demonstrate portfolio-wide shift away from fossil fuels. The AADFI Mapping Study (2024) recommends that green fund entities make the accreditation process "more friendly, speedy, and self-explanatory" and specifically calls for fast-tracking for member DFIs a recommendation the RAF partially addresses but does not fully resolve. |
| --- | --- |

| 4. The Simplified Approval Process (SAP): Opportunities and Limits The SAP was introduced in 2017 at the insistence of the SIDS Board member to provide faster access for vulnerable countries and smaller entities. Updated in 2022 to support financing up to USD 25 million for activities at minimal environmental and social risk, it functions as a streamlined pathway for proven, replicable climate interventions. By end-2025, 64 SAP projects worth USD 937.6 million had been approved. Opportunities: Shorter application templates, rolling review, and expedited post-approval arrangements. The Project Preparation Facility (PPF) provides up to USD 1.5 million per request to help entities particularly DAEs develop bankable proposals covering advisory, legal, and environmental costing services. The SAP is now the primary entry point for smaller national entities seeking their first GCF project. Year-round pre-screening allows DFIs to identify structural gaps before the formal cycle opens. Limits (IEU, 2025): The IEU evaluation concluded that the SAP pursued "simplified access rather than simple access" incremental procedural gains without resolving the institutional complexity that excludes the most capacity-constrained entities. Treichel et al. (2024) confirm the SAP had "not translated into simplified requirements or accelerated processes" for SIDS. The SAP still requires prior accreditation - the PSAA pilot allowing one project submission without full accreditation had approved only six proposals by early 2026, with a review at B.46 (October 2026). Owens et al. (2025) note just two of seven EDA proposals are in the Pacific. | 5. Where We Stand Now: Progress, Gaps, and Next Steps The GCF portfolio now totals USD 20.10 billion across 350 projects in 134 countries (total financing including co-financing: USD 79.86 billion). Record programming of USD 3.25 billion was achieved in 2025. Five regional offices were approved in March 2026. The readiness programme has approved 876 grants worth USD 740.71 million across 142 countries (USD 537.03 million disbursed). Yet only approximately USD 6.7 billion of USD 20.10 billion approved has reached the ground, and the DAE share of approved funding has remained near 20% for nearly a decade. AADFI evidence: The AADFI Mapping Study (2024) captured that, while 67.5% of African DFIs have attempted to access climate finance, only 7.5% have achieved GCF accreditation. The most requested support from AADFI is technical assistance for accreditation, capacity building for proposal development, advocacy with accreditation bodies to fast-track the process, and access to climate finance networks. This mirrors the structural persistence that reforms have not yet resolved: aspirations are high, institutional readiness remains low. Political and financial risks: The US withdrawal of ~USD 4 billion in pledges (January 2025) leaves GCF-2 confirmed pledges at USD 9.64 billion against a USD 10.64 billion target. The NCQG at COP 29 requires tripling annual VCEF outflows from 2022 levels by 2030. With GCF-3 replenishment launching mid-2026, institutional reform and adequate capitalisation must advance together. Priority next steps: (1) Cross-VCEF accreditation recognition - entities accredited by GEF or AF access GCF without full re-accreditation (COP 30 draft, Nov 2025); (2) multi-year sustained readiness investment targeting NDA/DAE capacity, not one-off grants; (3) PSAA pilot evaluation at B.46 (Oct 2026); (4) adoption of updated country ownership guidelines and gender action plan (2026); (5) restored GCF-3 pledges to meet the NCQG tripling commitment. |
| --- | --- |

6. Recommendations

- DFIs should apply to GEF or Adaptation Fund (AF) accreditation first. It is faster and simpler, and one completed project builds the track record that breaks the hurdle. Rwanda, Senegal, and Bangladesh have all used this route successfully.

- DFIs should engage GCF pre-screening before the application window opens to address the gaps.

- DFIs should apply for the Project Preparation Facility at the concept stage. Up to USD 1.5 million is available for data collection, legal fees, and assessments.

- DFIs should invest in climate finance staff expertise. Only 40% of African DFIs have dedicated staff.

- DFIs should engage their NDA before designing any project. The NDA holds knowledge of national priorities and funding gaps.

- The GCF should standardise Funded Activity Agreements so that legal arrangements are signed at the Board meeting itself, eliminating the months of post-approval delay that currently sit between a funding decision and the first disbursement reaching the ground.

- The two-month screening response window is too short for most AADFI member institutions to close fiduciary and ESS gaps, and the SAP still requires prior accreditation. The GCF should extend the response window for LDC and SIDS-based DFIs and expand the PSAA into a permanent project-first accreditation route before GCF-3 launches.

Sources: GCF Portfolio Dashboard & Readiness Data (greenclimate.fund, 2026) · Revised Accreditation Framework B.42/13 (Jul 2025) · GCF/B.44/Inf.08 (Jan 2026) · GCF DAE Readiness Guide (Sep 2025) · IEU SAP Evaluation No. 23 (2025) · AADFI/WFDFI Mapping Study (Nov 2024) · Treichel et al., Global Environmental Change 89 (2024) · Treichel et al., IIED Working Paper — The Promise of Direct Access to Climate Finance (May 2026) · Owens et al., Earth System Governance 24 (2025) · Germanwatch GCF-Focus Africa (Nov 2022) · IIED/ICCCAD Briefing (Sep 2015) · Achieng (Jul 2025) · GCFWatch/Böll Stiftung (May 2026).