GEF Research BRIEF  —  Centre for Sustainable Finance, SOAS University of London  ·  July 2026

GEF Accreditation to Disbursement: Barriers, Reforms & the Path Forward

Introduction

The Global Environment Facility (GEF) is the primary financial mechanism for five multilateral environmental agreements (MEAs) — covering biodiversity, climate change, land degradation, persistent organic pollutants, and mercury. Established as a World Bank pilot in 1991, it has evolved from a three-agency structure into a network of eighteen accredited agencies that has disbursed over $27 billion in grants across 170 countries, leveraging a further $155 billion in co-financing. Its 76% disbursement-to-approval ratio compares favourably with peer funds like the GCF (31%), yet the system has deep structural problems: accreditation costs that most developing-country national institutions simply cannot afford, disbursement timelines that have deteriorated sharply since GEF-7, and an institutional architecture that continues to concentrate resources in a handful of large multilaterals rather than the national agencies closest to project communities. GEF-9 (2026–2030) introduces the most substantive reform package in the facility’s history.

Key Statistics at a Glance

| $27B+ Total grants disbursed Across nine replenishment cycles | $155B+ Co-financing leveraged From governments, MDBs & private sector | 76% Disbursement ratio vs. GCF’s 31% — but deteriorating | 20 months Post-endorsement delay GEF-8 median — up from 9 months in GEF-7 | 18 Accredited agencies Up from 3 at founding in 1991 | 35% LDC/SIDS resource target GEF-9 commitment — highest ever |
| --- | --- | --- | --- | --- | --- |

| Replenishment Phases: GEF-1 to GEF-9 Phase; Key Change & Who Felt It. Pilot–GEF-2 1991–2002 ~$6.75B; Started as a World Bank pilot with only 3 agencies (World Bank, UNDP, UNEP) and entirely donor-directed programming. Restructured in 1994 as an independent fund with a governing Council and OFP system. Seven new Executing Agencies joined in GEF-2 (including AfDB), giving Sub-Saharan Africa its first direct MDB channel into the facility.. GEF-3/4 2003–2010 $6.26B; IEO established (2003). Project approval backlog peaked at 4+ years under first-come queuing. The Resource Allocation Framework (RAF) was introduced in GEF-4 to assign country-specific envelopes — a structural improvement, but the bottleneck simply shifted upstream to the national level rather than being resolved.. GEF-5 2010–2014 $4.34B; STAR replaced RAF, giving countries full flexibility over focal area allocations. A pilot accreditation programme launched: up to 10 new Project Agencies allowed. Only 8 of 11 applicants succeeded. DBSA (South Africa) became the first national developing-country institution to be accredited — 20 years after GEF’s founding.. GEF-6/7 2014–2022 $8.53B; 18 agencies fully operational; new agencies captured 8% of the GEF-6 portfolio. Agency expansion paused in GEF-7. Thematic shift toward integrated multi-focal programmes. GBFF established. UNDP’s share rose to 33.4% of GEF-8 resources while all regional agencies combined fell to just 3.2%.. GEF-8 2022–2026 $5.30B; A genuine improvement in pre-endorsement efficiency: CEO endorsement reached an 18-month median (73% on-time, up from 14% in GEF-7). But this was undermined by a sharp post-endorsement slowdown: median first disbursement took 20 months — more than double the 9 months recorded in GEF-7. GBFF operationalised.. GEF-9 2026–2030 $3.9B*; Most reform-intensive cycle: fast-track accreditation for GCF/AF-accredited entities; 30-month disbursement cancellation rule; 25% portfolio cap per agency; 35% LDC/SIDS allocation; 43% of STAR ring-fenced; new disbursement efficiency sub-index; BBNJ Agreement integrated. Initial pledges lower than GEF-8 peak, but more pledges expected.. *Initial pledges as of July 2026; additional contributions expected at 2026 COP processes. GEF-9 Reforms & Recommendations GEF Fund - GEF-9 fast-tracks GCF and Adaptation Fund-accredited entities past Stage 2, bypassing full fiduciary re-review. An independent panel will target institutions in LDC/SIDS coverage gaps, with recommendations due June 2027. - The 30-month cancellation rule automatically returns inactive project resources to the country’s programming envelope — addressing the post-endorsement paralysis problem directly. - To go further: cap the true accreditation cost at $50K via a Secretariat-funded TA package. Introduce regional cluster applications for sub-regional groups of NDBs. Issue all GEF Portal templates and Terminal Evaluation forms in French, Portuguese, and Spanish as standard.; Agencies & National Institutions - De-link GEF grants from MDB sovereign loan timelines. Grants should become legally effective independently of loan signing, with disbursement held pending a lightweight parallel readiness confirmation. - Accept board-approved MDB programming decisions (not signed loan agreements) as co-financing at CEO Endorsement — this closes the gap between commitment and actual execution. - Require the original three agencies to formally partner with a national or regional LDC/SIDS institution on every project above $5M, building the track record the Panel weights most. National institutions: seek SGP executing agency status before applying for full accreditation.. Key Abbreviations ADB — Asian Development Bank; AfDB — African Development Bank; CBD — Convention on Biological Diversity; CEO — GEF Chief Executive Officer. DBSA — Development Bank of Southern Africa; ESS — Environmental & Social Safeguards; FAO — Food & Agriculture Organization; FPIC — Free, Prior and Informed Consent. GBFF — Global Biodiversity Framework Fund; GCF — Green Climate Fund; GEF — Global Environment Facility; IADB — Inter-American Development Bank. |  | The Accreditation Process: Three Stages Stage 1 — Strategic Review - Operational Focal Point (OFP) endorses the institution. Secretariat assesses relevance, track record, geographic reach, and co-financing capacity. Council formally approves the shortlist. - Country can nominate one to two institutions per replenishment cycle. Stage 1 is relatively accessible — the harder gates come later. GEF-5 pilot: 11 applicants submitted → 8 passed Stage 1.; Stage 2 — Fiduciary Review - Non-refundable $25,000 application fee — but actual institutional cost runs $200K–$500K once legal, advisory, and systems upgrade costs are counted. An independent 3-member Accreditation Panel reviews audit integrity, internal controls, procurement systems, and whistleblower protections. - Average review time: 7 months against a policy target of 2–3 months. First 5 accredited agencies spent ~$2.3M combined; only 15% was recovered through fees.; Stage 3 — Safeguards & Formalisation - Compliance review covering Environmental & Social Safeguards (ESS), gender mainstreaming policies, and stakeholder engagement including Free, Prior and Informed Consent (FPIC). Completed by an MoU with the Secretariat and a Financial Procedures Agreement with the World Bank Trustee to activate direct fund transfers. 2016 evaluation: GEF ESS lacked human rights and FPIC coverage, creating friction with GCF’s IFC Performance Standards — applicants serving both funds faced contradictory requirements.. Challenges: Accreditation, Disbursement & Who Bears the Burden Accreditation barriers - Access paradox: national institutions in LDCs and SIDS cannot demonstrate compliance with fiduciary standards without prior experience managing large international funds — but getting that experience requires accreditation in the first place. The catch-22 has locked out national agencies for 35 years. - True cost ($200K–$500K) is prohibitive for most national institutions. In GEF-5, only 2 of 10 targeted agencies completed accreditation; the 10 projects they collectively implemented totalled $47M — less than 2% of the cycle’s portfolio. - Portfolio concentration: UNDP held 33.4% of GEF-8 resources; all regional agencies combined held 3.2%, down from 5.6% in GEF-7. Despite the GEF’s stated diversification objective, the gap widened. GEF-9 introduces a 25% per-agency portfolio cap to address this. - Standard misalignment: GEF ESS diverges from GCF’s IFC Performance Standards, creating duplicative and sometimes contradictory compliance requirements for institutions seeking access to both funds. Language barriers also persist: English-only documentation excludes many Francophone and Lusophone national institutions. Disbursement delays by agency — GEF-5 cohort (579 projects endorsed) Agency; Year 1; Year 2; Year 3. UNIDO; 100%; 100%; 100%. UNEP; 86%; 92%; 95%. FAO; 71%; 90%; 90%. World Bank; 55%; 89%; 93%. AfDB; 0%; 50%; 50%. IADB; 26%; 79%; 79%. ADB; 33%; 52%; 62%. IFAD; 22%; 44%; 78%. Root causes of post-endorsement delay: - MDB grants are legally tied to sovereign loan negotiations and internal board approvals. Until the bank’s loan is signed, the GEF grant cannot disburse — even if the project is technically ready. - Co-financing commitment letters are required at CEO Endorsement, forcing governments and MDBs to lock in resources 2–3 years before implementation actually starts. Any change triggers resubmission. - GEF-8 median first disbursement: 20 months — up from 9 months in GEF-7 and 11 months in GEF-6. Child projects under Integrated Programs face the longest delays due to multi-stakeholder governance setup requirements. |
| --- | --- | --- |